NJ Early Intervention System (NJEIS) CORRECTIVE ACTION PLAN (CAP)

TO ADDRESS SYSTEMIC NONCOMPLIANCE

| NJEIS Contact | Agency Name | Date CAP Requested | Date CAP Due to NJEIS |
| --- | --- | --- | --- |
|  |  | 10-6-2011 | 11-1-2011 |

- Areas of Noncompliance

- Failure to implement service coordination responsibilities

“Specific service coordination activities.”

Service coordination activities include – Facilitating the development of a transition plan to preschool services, if appropriate (34 CFR 303.23(b) (7)).

- Failure to meet transition timelines

Transition procedures did not ensure that a meeting where appropriate, was held 90 days prior to the child’s third birthday (34 CFR 303.148(b) (2) (i)).

- Finding/Supportive Evidence:

According to SPOE data and the SCU Inquiry Report submitted in June, 2011, 76.92% of Transition Planning Conference (TPC) meetings were held at least 90 days prior to a child’s third birthday for February, March and April 2011.   However, 23.08% of the TPC meetings did not occur 90 days prior to a child’s third birthday.

Corrective Actions:  Complete the following to detail the actions your agency will take to correct the noncompliance in a timely manner.  This CAP must be submitted to NJEIS for approval by November 1, 2011.  All noncompliance must be corrected by June 30, 2012 in accordance with the evidence of change statements provided below.

| Corrective Action | Strategies | Who is responsible? | Timeline |
| --- | --- | --- | --- |
| Development/Revisions to Service Coordination Unit (SCU) Procedures |  |  |  |
| Infrastructure/Staffing |  |  |  |
| Provisions of Training |  |  |  |
| Provision of Technical Assistance |  |  |  |
| Changes to Supervision |  |  |  |

| Required Evidence of Change | Date To Be Completed |
| --- | --- |
| On each subsequent month, document the current status of the TPC for each reporting month. Baseline 76.92% compliance The required targets for compliance are: As of 11/30/11 for children who turn 3 in February 2012 80% compliance Report due 11/30/11 As of 12/30/11 for children who turn 3 in March 2012 85% compliance Report due 12/30/11 As of 1/30/12 for children who turn 3 in April 2012 90% compliance Report due1/30/12 As of 2/28/12 for children who turn 3 in May, 2012 95% compliance Report due 2/28/12 As of 3/30/12 for children who turn 3 in June , 2012 100% compliance Report due 3/30/12 No evidence of systemic non-compliance | Monthly Summary Reports submitted to NJEIS beginning November 30,2011 |

Signatures of individuals completing report 					Agency and Title					Date

CAP to be submitted by November 1, 2011 to                         , EIS Monitoring Officer

Signature, Title and Date the report was accepted by NJEIS

|  | EIS Monitoring Officer New Jersey Early intervention System |  |
| --- | --- | --- |